## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [7 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Home Usage Power Detector |  |  |  |  | COMPANY NAME | [8 empty] | Thai-Nichi Institude of Technology | [24 empty] | กำหนดการ
PROJECT MANAGER |  | Siratee Tanjoy |  |  |  |  | DATE | [8 empty] | 17/1/25 | [24 empty] | เสร็จจริง
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [20 empty] | PHASE TWO | [20 empty] | PHASE THREE | [20 empty] | PHASE FOUR
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
[7 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
1 | Project Proposal
1.1 | ศึกษาหัวข้อที่จะทำ | Siratee | 20/12/24 | 23/12/24 | 4 | 100% | bar: WEEK 1 Fri to WEEK 2 Mon
|  |  | 20/12/24 | 23/12/24 | 4 | 100% | bar: WEEK 1 Fri to WEEK 2 Mon
1.2 | ศึกษาอุปกรณ์ที่จะใช้ | Siratee | 20/12/24 | 26/12/24 | 7 | 100% | bar: WEEK 1 Fri to WEEK 2 Thu
|  |  | 20/12/24 | 26/12/24 | 7 | 100% | bar: WEEK 1 Fri to WEEK 2 Thu
1.3 | นัดคุยปรึกษาอาจารย์ 1 | Siratee | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 Mon
|  |  | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 Mon
2 | กำหนดขอบเขต
2.1 | ยืนยันกำหนดงบประมาณ | Steve L | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 Mon
|  |  | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 Mon
2.2 | กำหนดขอบเขตโครงงาน | Siratee | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 Mon
|  |  | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 Mon
2.3 | กำหนดอุปกรณ์ที่จะใช้ | Siratee | 23/12/24 | 26/12/24 | 4 | 100% | bar: WEEK 2 Mon to WEEK 2 Thu
|  |  | 23/12/24 | 26/12/24 | 4 | 100% | bar: WEEK 2 Mon to WEEK 2 Thu
3 | เตรียมอุปกรณ์
3.1 | ขอเบิกอุปกรณ์จากอาจารย์ | Siratee | 24/12/24 | 24/12/24 | 1 | 100% | bar: WEEK 2 Tue
|  | Siratee | 27/12/24 | 27/12/24 | 1 | 100% | bar: WEEK 2 Fri
3.2 | สั่งซื้ออุปกรณ์
3.2.1 | สั่งซื้ออุปกรณ์ | Siratee | 25/12/24 | 26/12/24 | 2 | 100% | bar: WEEK 2 Wed
| อุปกรณ์เริ่มจัดส่ง |  | 2025-02-01 | 2025-04-01 | 2 | 100% | bar: WEEK 3 Thu to WEEK 3 Fri
3.2.2 | สั่งซื้ออุปกรณ์เพิ่มเติม | Siratee | 13/1/25 | 13/1/25 | 1 | 100% | bar: WEEK 5 Mon
| อุปกรณ์เพิ่มเติมเริ่มจัดส่ง |  | 13/1/25 | 14/1/25 | 2 | 100% | bar: WEEK 5 Mon to WEEK 5 Tue
4 | พัฒนาโครงงาน
4.1 | ทดลองและศึกษาการใช้งานอุปกรณ์ | Siratee | 2025-04-01 | 2025-12-01 | 0 | 100% | bar: WEEK 3 Fri to WEEK 4 Sun
|  |  | 2025-04-01 | 17/1/25 | 0 | 75% | bar: WEEK 3 Fri to WEEK 5 Fri
4.2 | ออกแบบโค้ดของโครงงาน
4.2.1 | ส่วนของการวัดแสง | Siratee | 13/1/25 | 15/1/25 | 3 | 100% | bar: WEEK 5 Mon to WEEK 5 Wed
[5 empty] | 0 | 0%
4.2.2 | ส่วนของการวัดอุณหภูมิ | Siratee | 16/1/25 | 22/1/25 | 7 | 100% | bar: WEEK 5 Thu to WEEK 6 Wed
[5 empty] | 0 | 0%
4.2.2.1 | Project update | Siratee | 22/1/25 | 22/1/25 | 1 | 100% | bar: WEEK 6 Wed
|  |  | 22/1/25 | 22/1/25 | 1 | 0%
4.2.2.2 | Update project plan | Siratee | 24/1/25 | 24/1/25 | 1 | 100% | bar: WEEK 6 Fri
|  |  |  | 24/1/25 | 1 | 0%
4.2.3 | ส่วนของการวัดการใช้ไฟฟ้า | Siratee | 22/1/25 | 2025-01-02 | 11 | 100% | bar: WEEK 6 Wed to WEEK 7 Sat
[5 empty] | 0 | 0%
4.2.3.1 | Project update 2 | Siratee | 2025-05-02 | 2025-05-02 | 1 | 100% | bar: WEEK 8 Wed
|  |  | 2025-05-02 | 2025-05-02 | 1 | 0%
4.2.3.2 | Update project plan 2 | Siratee | 2025-07-02 | 2025-07-02 | 1 | 100% | bar: WEEK 8 Fri
|  |  | 2025-07-02 | 2025-07-02 | 1 | 0%
4.3 | สร้างdashboardสรุปการตรวจจับต่างๆ | Siratee | 2025-01-02 | 2025-12-02 | 12 | 100% | bar: WEEK 7 Sat to WEEK 9 Fri
0%
5 | นำเสนอโครงงาน
5.1 | Final project files submit | Siratee | 19/2/25 | 19/2/25 | 1 | 100% | bar: WEEK 10 Wed
|  |  | 19/2/25 | 19/2/25 | 1 | 0%
5.2 | Present project | Siratee | 21/2/25 | 21/2/25 | 1 | 100% | bar: WEEK 10 Fri
|  |  |  | 21/2/25 | 1 | 0%