## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [7 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Home Usage Power Detector |  |  |  |  | COMPANY NAME | [8 empty] | Thai-Nichi Institude of Technology | [24 empty] | กำหนดการ
PROJECT MANAGER |  | Siratee Tanjoy |  |  |  |  | DATE | [8 empty] | 17/1/25 | [24 empty] | เสร็จจริง
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [20 empty] | PHASE TWO | [20 empty] | PHASE THREE | [20 empty] | PHASE FOUR
[7 empty] | WEEK 1 (Dec) | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 (Jan) | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 (Feb) | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 (Mar) | [6 empty] | WEEK 12
[7 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
[7 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
1 | Project Proposal
1.1 | ศึกษาหัวข้อที่จะทำ | Siratee | 20/12/24 | 23/12/24 | 4 | 100% | bar: WEEK 1 (Dec) 20 Fri to WEEK 2 23 Mon
|  |  | 20/12/24 | 23/12/24 | 4 | 100% | bar: WEEK 1 (Dec) 20 Fri to WEEK 2 23 Mon
1.2 | ศึกษาอุปกรณ์ที่จะใช้ | Siratee | 20/12/24 | 26/12/24 | 7 | 100% | bar: WEEK 1 (Dec) 20 Fri to WEEK 2 26 Thu
|  |  | 20/12/24 | 26/12/24 | 7 | 100% | bar: WEEK 1 (Dec) 20 Fri to WEEK 2 26 Thu
1.3 | นัดคุยปรึกษาอาจารย์ 1 | Siratee | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 23 Mon
|  |  | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 23 Mon
2 | กำหนดขอบเขต
2.1 | ยืนยันกำหนดงบประมาณ | Titichaya | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 23 Mon
|  |  | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 23 Mon
2.2 | กำหนดขอบเขตโครงงาน | Siratee | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 23 Mon
|  |  | 23/12/24 | 23/12/24 | 1 | 100% | bar: WEEK 2 23 Mon
2.3 | กำหนดอุปกรณ์ที่จะใช้ | Siratee | 23/12/24 | 26/12/24 | 4 | 100% | bar: WEEK 2 23 Mon to WEEK 2 26 Thu
|  |  | 23/12/24 | 26/12/24 | 4 | 100% | bar: WEEK 2 23 Mon to WEEK 2 26 Thu
3 | เตรียมอุปกรณ์
3.1 | ขอเบิกอุปกรณ์จากอาจารย์ | Siratee | 24/12/24 | 24/12/24 | 1 | 100% | bar: WEEK 2 24 Tue
|  | Siratee | 27/12/24 | 27/12/24 | 1 | 100% | bar: WEEK 2 27 Fri
3.2 | สั่งซื้ออุปกรณ์
3.2.1 | สั่งซื้ออุปกรณ์ | Siratee | 25/12/24 | 26/12/24 | 2 | 100% | bar: WEEK 2 25 Wed
| อุปกรณ์เริ่มจัดส่ง |  | 2025-02-01 | 2025-04-01 | 2 | 100% | bar: WEEK 3 (Jan) 2 Thu to WEEK 3 (Jan) 3 Fri
3.2.2 | สั่งซื้ออุปกรณ์เพิ่มเติม | Siratee | 13/1/25 | 13/1/25 | 1 | 100% | bar: WEEK 5 13 Mon
| อุปกรณ์เพิ่มเติมเริ่มจัดส่ง |  | 13/1/25 | 14/1/25 | 2 | 100% | bar: WEEK 5 13 Mon to WEEK 5 14 Tue
4 | พัฒนาโครงงาน
4.1 | ทดลองและศึกษาการใช้งานอุปกรณ์ | Siratee | 2025-04-01 | 2025-12-01 | 10 | 100% | bar: WEEK 3 (Jan) 3 Fri to WEEK 4 12 Sun
|  |  | 2025-04-01 | 18/1/25 | 16 | 100% | bar: WEEK 3 (Jan) 3 Fri to WEEK 5 18 Sat
4.2 | ออกแบบโค้ดของโครงงาน
4.2.1 | ส่วนของการวัดแสง | Siratee | 13/1/25 | 15/1/25 | 3 | 100% | bar: WEEK 5 13 Mon to WEEK 5 15 Wed
|  |  | 20/1/25 | 22/1/25 | 3 | 100% | bar: WEEK 6 20 Mon to WEEK 6 22 Wed
4.2.2 | ส่วนของการวัดอุณหภูมิ | Siratee | 16/1/25 | 22/1/25 | 7 | 100% | bar: WEEK 5 16 Thu to WEEK 6 22 Wed
|  |  | 21/1/25 | 22/1/25 | 2 | 100% | bar: WEEK 6 21 Tue to WEEK 6 22 Wed
4.2.2.1 | Project update | Siratee | 22/1/25 | 22/1/25 | 1 | 100% | bar: WEEK 6 22 Wed
|  |  | 22/1/25 | 22/1/25 | 1 | 100% | bar: WEEK 6 22 Wed
4.2.2.2 | Update project plan | Siratee | 24/1/25 | 24/1/25 | 1 | 100% | bar: WEEK 6 24 Fri
|  |  | 24/1/25 | 24/1/25 | 1 | 100% | bar: WEEK 6 24 Fri
4.2.3 | ส่วนของการวัดการใช้ไฟฟ้า | Siratee | 22/1/25 | 2025-01-02 | 11 | 100% | bar: WEEK 6 22 Wed to WEEK 7 (Feb) 1 Sat
|  |  | 26/1/25 |  | 6 | 95% | bar: WEEK 6 26 Sun to WEEK 8 3 Mon
4.2.3.1 | Project update 2 | Siratee | 2025-05-02 | 2025-05-02 | 1 | 100% | bar: WEEK 8 5 Wed
|  |  | 2025-05-02 | 2025-05-02 | 1 | 100% | bar: WEEK 8 6 Thu
4.2.3.2 | Update project plan 2 | Siratee | 2025-07-02 | 2025-07-02 | 1 | 100% | bar: WEEK 8 7 Fri
|  |  | 2025-07-02 | 2025-07-02 | 1 | 0% | bar: WEEK 8 7 Fri
4.3 | สร้างdashboardสรุปการตรวจจับต่างๆ | Siratee | 2025-01-02 | 2025-12-02 | 12 | 100% | bar: WEEK 7 (Feb) 1 Sat to WEEK 9 14 Fri
[5 empty] | 0 | 4% | bar: WEEK 8 3 Mon to WEEK 10 21 Fri
5 | นำเสนอโครงงาน
5.1 | Final project files submit | Siratee | 19/2/25 | 19/2/25 | 1 | 100% | bar: WEEK 10 19 Wed
|  |  | 19/2/25 | 19/2/25 | 1 | 0%
5.2 | Present project | Siratee | 21/2/25 | 21/2/25 | 1 | 100% | bar: WEEK 10 21 Fri
|  |  | 19/2/25 | 21/2/25 | 1 | 0%